Type of Review: Annual Review

Project Title: Strengthening South Africa’s Response to HIV and Health (SARRAH)

Date started: Jan 2010	Date review undertaken: 28 May – 1 June 2012

## Introduction and Context

What support is the UK providing?
SARRAH is a 5 year programme, it commenced in January 2012 and is due to end in December 2014. The total committed funds are £20,352,215.06

What are the expected results?
The impact[1] of this programme is to ‘meet MDG 6 targets in South Africa through delivery of the South African National Strategic Plan on HIV, AIDS and STIs (NSP) 2007-2011 and its successor’. Progress is expected against the following indicators: / HIV prevalence among 15-24 year old women and girls / HIV prevalence among 15 – 49 year old women / HIV Incidence among women (15-24) / Death from all causes 25-29 (gender disaggregated) / Under 5 child mortality and maternal mortality indicator ratio / The expected outcome[2] is ‘improved governance of an integrated, effective response to HIV & AIDS and health in South Africa’. Progress is expected against the following indicators: / UNGASS national composite policy index / % of fully immunized children <1year / Number of new patients (adults and children) initiated on ARVs / % cases treated successfully out of all estimated TB cases (all forms of disease) for a given period / Improved donor coordination and harmonisation
[1] ‘Impact’ is the DFID preferred term for the overall ‘goal’ (as used in the current logframe).
[2] ‘Outcome’ is the DFID preferred term for the overall ‘purpose’ (as used in the logframe).

What is the context in which UK support is provided?
The SARRAH programme was initiated at a time when the South African health system was emerging from a period of controversial management, particularly with regard to HIV and AIDS. During President Mbeki’s tenure the Department of Health was adversely influenced by the ‘AIDS denialists’ and HIV and AIDS services were severely compromised as a result. For example, the roll-out of life-saving antiretroviral (ARV) treatment was painfully slow. One of the current SARRAH partners, the Treatment Action Campaign, gained international acclaim for its successful legal challenge which forced the government to make ARVs more widely available. The changes of leadership which followed the recall of President Mbeki created an opportunity for donors to work on health matters with the South African government once again and SARRAH was designed to make the most of this opportunity. The Government’s commitment to achieving a long and healthy life for all South Africans is outlined in the National Service Delivery Agreement (NSDA) targets. The high level of commitment to transforming the health sector is perhaps best illustrated in the increased budget for the health sector, which in 2011/12 totalled Rand 25.3 billion, an increase of 90% from just four years ago. / The SARRAH programme is not a single large-scale intervention, but supports national reforms, programmes and institutions of the South African health sector through a range of strategic interventions identified jointly by DFID and NDoH. This has led SARRAH to diversify into a range of activities, each supporting different parts of the policy landscape and each intervening at different levels in the line of management. SARRAH’s alignment to the NDoH 10 Point Health Plan, the policy instrument through which the NSDA will be achieved, is demonstrated in Figure 1. While all workstreams are working towards the same overarching goal, the diversity is such that each workstream could be considered as an intervention in itself. / Fig. 1. SARRAH’s technical work streams (boxes) in support of the 10-Point Health Plan (SARRAH Quarterly Report January to March 2012, p3) / The context of a new era of opportunity which characterised the start of SARRAH remains and the climate for improvements in the South Africa health system remains positive. Equitable access to health care is a major policy driver for the ANC government, opposition parties and organised labour and is therefore almost certain to remain a priority.

## Section A: Detailed Output Scoring

Output 1: enable the improvement in quality of and access to HIV & AIDS and health services in selected districts
Output 1 score and performance description: A / SARRAH’s contribution to this Output to date has focused on interventions to prevent mother-to-child transmission of HIV (PMTCT) which were successful but concluded in June 2011. At that time MTCT had achieved the 2012 Milestone according to an MRC study (3.6%) and since then has further improved to 2.89% by February 2012, National Health Laboratory Services (NHLS).
Progress against expected results: / Progress against expected results: / Indicator 1: Transmission rate of MTCT (A+) / 2012 Milestone: 4% / 2012 Actual: This work was completed in June 2011 at which time the national MTCT rate was 3.5%. By February 2012, the national average was 2.89% (NHLS, Feb 2012). / Indicator 2: Utilisation rate of Primary Health Care facilities (B) / 2012 Milestone: 3.1 visits per capita / 2012 Actual: Although the PHC revitalisation agenda is moving forward, implementation of improvement interventions in the pilot districts has not yet started, although some pilot districts have started the recruitment process for the implementation teams. The 2010/11 District Health Information System (DHIS) reports a utilisation rate of 2.4 visits per capita. / Indicator 3: Antenatal visits before 20 weeks rate (A+) / 2012 Milestone: 38.5% / 2012 Actual: The 2011/12 DHIS reports a rate of 40.2% indicting that this milestone was exceeded, despite the PHC revitalisation interventions not having started yet. / Indicator 4: Utilisation rate (visits), children under 5 years (annualised) / 2012 Actual: Not available / Recommendations / Specific activities in terms of prevention of mother-to-child HIV transmission ended in June 2011. Further roll-out of the PMTCT A-plan is dependent on the NDOH and does not currently involve SARRAH. Although future milestones for this indicator will reflect sustainability of the SARRAH intervention, the relationship becomes more tenuous over time. It may be appropriate to drop the PMTCT-specific milestone (1) and revisit the more general PHC ones (2 - 4) only when the Quality Improvement of PHC facilities and/or NHI is started in the selected districts. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? N

Output 2: Strengthened leadership and accountability of the national response to HIV and AIDS
Output 2 score and performance description: A / The 2011 Annual Review recommended that SARRAH reconsider support to both TAC and SANAC. TAC was struggling to find its raison d’etre within a new context where space existed for policy dialogue with government and this struggle was compounded by a negative external compliance review. SANAC was struggling to establish itself as the national coordinating mechanism, and had suffered a loss of leadership. In the subsequent year both organisations have made remarkable progress. A new SANAC CEO was appointed in February and has already: secured Board approval (on 4th June) for a new organisational structure and a focus on provinces; reinvigorated and reorganised SANAC’s governance structures – including getting buy-in up to the level of Deputy President; and is dealing with financial and HR management challenges. TAC has managed to meet all this year’s Milestones whilst going through a process of reorganisation and retrenchment. With support from SARRAH it has developed a new Business Plan (2012-15) which puts its membership base at its heart. It will provide district structures with the skills, tools and capacities to advocate at a local level and draw on the knowledge and activism of this membership base to feed into national level policy formulation. As part of its strategy towards financial sustainability TAC is currently in the process of establishing an Activist Centre which will be a ‘college for activist education’ using TAC experience as a case study for how policy can be influenced by coordinated activist movements. / The Joint Committee on HIV and AIDS held its first meeting on March 24th. In order to support Parliamentary oversight of HIV and AIDS within the broader framework of the health sector HLSP prepared a report (in February 2012) proposing future SARRAH support is focused on the three main parliamentary oversight committees for health – the Portfolio Committee on Health, the Select Committee on Social Services and the Joint Committee on HIV and AIDS.
Progress against expected results: / Indicator 1: SANAC (South African National AIDS Council) Secretariat established and functional (A) / 2012 Milestone: SANAC secretariat lead formulation and publication of NSF 2012/2016 including final review of 2007 – 11 NSP / 2012 Actual: The National Strategic Plan on HIV, STIs and TB 2012 – 2016 (NSP) was published on 1st December 2011. The development of the NSP was led by the SANAC secretariat, the Programme Implementation Committee and staff of the Department of Health and contributions were made by SANAC sectors, task teams and individuals who contributed more than 100 written submissions. SARRAH provided technical assistance. / 2012 Milestone: SANAC functions as an independent entity / 2012 Actual: The Milestone is no longer relevant as SANAC does not need to be an independent entity, which was seen as necessary in the ‘HIV denialist era’, but will continue to operate under the purview of NDOH. Since the appointment of the new SANAC CEO in February 2012, the SANAC Plenary, Chaired by the Deputy President, has approved new SANAC organisational and governance structures including four new Technical Task Teams aligned to the NSP plus a Research Task Team and an NSP Financing Committee, the latter comprising, among others, six Deputy Ministers. The Board of Trustees has signed off on SANAC banking arrangements to operate the South African National AIDS Trust Account, a CFO has been recruited and an Executive Manager for NSP Implementation has been appointed. The Board has also approved a SANAC budget for the next three years and 13 of 21 positions within the organisational structure are funded. Provinces will be front and centre of the newly refocused SANAC. The Deputy President, Minister of Health and 9 Premiers reviewed the SANAC structure prior to submission to the SANAC plenary on 1 June to ensure buy-in. / 2012 Milestone: Revised NAC (CCM) structure defined and established to support GFATM applications and grants / 2012 Actual: The SANAC Remunerations Committee has been restructured with a subcommittee specifically looking at GFATM. The committee will be able to meet all the requirements of GFATM in July 2012. / 2012 Milestone: Costed new NSP in place published after consultative process. / 2012 Actual: The NSP costing summary covers all known key cost drivers – some interventions and strategies are uncosted as apparently no costing was possible. / Indicator 2: All Party Parliamentary Oversight Committee established and functional (A) / 2012 Milestone: Mechanism for engaging Parliament agreed and two public hearings supported / 2012 Actual: Members of the Joint Committee on HIV and AIDS were elected in March, the Committee has representatives from the National Assembly and the Council of Provinces.[3] About 60% of the members of this committee are also members of the Health Portfolio Committee. The Joint Committee held its first meeting on 24th May 2012. / Indicator 3: TAC (Treatment Action Campaign) quarterly progress monitoring of the NSP/NSF (B) / 2012 Milestone: M&E system developed and aligned to NSP and Quarterly Reviews informed by TAC data. / 2012 Actual: TAC’s M&E system was developed and in place in 2011, however, subsequently TAC has gone through a process of restructuring. A new business plan is in place and an M&E roadmap developed to support alignment of the M&E system to the new business plan – which is linked to monitoring of the NSP. Appropriate targets have been set, with the support of HLSP, but the M&E system is not yet fully operational. / 2012 Milestone: External DFID audit complete / 2012 Actual: The audit was completed during the second quarter of 2011 and substantial improvements were noted. SARRAH support of TAC continued as a result. / Indicator 4: Number of citizens supported by TAC to hold government to account for commitments made in the NSP (National Strategic Plan)/NSF (A) / 2012 Milestone: 81,000 / 2012 Actual: As of the end of September 2011 TAC has supported 54,033 citizens to hold government to account for NSP commitments. At the time of the review the latest quarterly report was incomplete but the TAC Chief Operations Officer estimated the number of people mobilised in TAC activities as greater than 81,000. Active membership, which utilises a mobile phone subscription system, was estimated at 6,000 in 6 Provinces. / Indicator 5: Effective lobbying and advocacy of government on key issues in relation to HIV and health (A+) / 2012 Milestone: 2 submissions (NHI and NSP 2012-2016) / 2012 Actual: In collaborations with Section 27 TAC produced an NSP review document.[4] TAC has also produced: an NHI review document; [5] a paper on the functioning of AIDS Councils; and, as part of a national campaign of ‘16 days activism against women and children abuse’, Women’s Health/Gender-Based Violence maps which provide details of services in model districts. / Indicator 6: Number of rape survivors who access Post Exposure Prophylaxis (A+) / 2012 Milestone: 50% TAC linked PHC facilities providing comprehensive PEP services / 2012 Actual: Currently 59% of facilities where TAC has a presence (70 out of 120) are providing comprehensive PEP services and programmes. / Recommendations: / SANAC, TAC and Parliament provide critical oversight and accountability functions with respect to Government’s implementation of the NSP and strategic support to help them fulfil this mandate is essential for ensuring long term sustainability of SARRAH’s interventions in support of the NSP. / Continued SARRAH support for TAC, SANAC and Parliament is recommended. If new funding is committed SARRAH’s logframe should be amended to reflect the new strategic direction of SANAC and TAC and new support to three Parliamentary committees. / The indicator related to gender under the support to TAC (Provision of Post-exposure Prophylaxis) is not directly related to TAC activities. TAC’s gender specific work could be better reflected in an indicator related to advocacy on gender-based violence. / Impact Weighting (%): 30% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? N
[3] South Africa. 24 May 2012. Parliament forms joint Committee on HIV and AIDS. http://www.info.gov.za/speech/DynamicAction?pageid=461&sid=27728&tid=69610
[4] # SECTION27. 1 Dec 2011. TAC and SECTION27 release the first issue of our magazine: NSP Review. http://section27.org.za.dedi47.cpt1.host-h.net/2011/12/02/tac-and-section27-release-the-first-issue-of-our-magazine-nsp-review/
[5] SECTION27, 6 Dec 2011. Understanding National Health Insurance in South Africa. http://www.section27.org.za/NHI/

Output 3: Support national interventions to improve access and equity to HIV and health services
Output 3 score and performance description: B / The overall score, B (output moderately did not meet expectation) reflects the delays to the NHI, SAHPRA and OHSC legislative processes against expected milestones (which were set by government and no doubt ambitious). In the case of OHSC and SAHPRA high quality technical inputs have lain foundations for strong institutions when legislation is passed. / However, SARRAH has implemented a wealth of additional work under this output, most of which relates to preparation for National Health Insurance (NHI). The Minister of Health has publicly stated that improving quality in public health is a precondition for NHI survival. SARRAH is supporting interventions which lay foundations for improved health care at district level. SARRAH has provided technical papers to inform NHI Ministerial Advisory Committee deliberations on the institutional set up of NHI. SARRAH has enabled broad consultation on NHI with both with South African technical experts and local stakeholders. / This support to root and branch strengthening of the South African health system will be invaluable to improving health outcomes no matter what the eventual outcome of the NHI debate. That said, all interviewees shared the view that the ruling ANC party is firmly committed to NHI and concur that it will be implemented. International delegates at the Midrand conference on NHI, supported by SARRAH, contributed evidence in support of a more realistic time frame to achieve universal access, namely 14 years. / SARRAH’s rapid logistical and technical support has enabled consultation through the ongoing ministerial roadshow with representatives of large numbers of stakeholder groups at district level. The level of commitment shown by the minister (spending 30 days in the pilot districts) is comparable to the number of days candidates spend campaigning in UK parliamentary elections. This demonstrates an exceptional level of commitment to the initiative and SARRAH’s support has been vital to facilitating this process.
Progress against expected results: / Indicator 1: Progress toward the establishment of the NHI (National Health Insurance) (A) / 2012 Milestone: Draft bill for NHI published for public comment / 2012 Actual: The Green Paper was gazetted for public comment in August 2011. The target for the White Paper is September 2012. / SARRAH provided logistical support to the NHI Ministerial Advisory Committee (MAC) and a series of technical papers to inform MAC deliberations. These covered benefit package design; purchasing provider payment mechanisms and price determinations; and an investigation of capitation payments. / 2012 Milestone: NHI started in pilot districts / 2012 Actual: 10 Pilot Districts were announced in March 2012. / SARRAH assisted with the selection of pilot districts for the NHI by providing a briefing paper proposing criteria for the selection of pilot districts and a paper on options for District Health Authorities.[6] SARRAH prepared a ToR for secretariat support to the NHI Pilot Advisory Committee designed to enable pilot districts to draw on national expertise. / HLSP seconds a Technical Lead Dr Gugu Ngubane, full time to the office of the Director General. A facility audit of 4,300 facilities to assess against 6 core quality standards in 7 domains of health care was carried out. Dr Ngubane assisted through preparation of ToR for Health Facility Improvement Teams (FIT) and overall coordination of the project, including coordination of four new Facility Improvement Teams that will prepare an improvement plan for each district. / In order to secure buy-in to the NHI from key stakeholders, the Minister has embarked on a road show where he spends 3 days in each district introducing NHI to groups including GPs, mayors, traditional leaders, religious groups, school principals, health workers, teachers’ unions, facility managers, NGOs and media. In each district closed meetings are held with each group and the Minister presents the NHI and takes questions. This was underway at the time of this review. SARRAH is providing logistical support to this process. / SARRAH drafted guidance on the Ministerial District Clinical Specialist Teams, which aim to reduce maternal and child mortality. The purpose of the team is to improve clinical governance at a higher level by preparing clinical guidelines and training doctors. The teams should comprise an obstetrician, gynaecologist, paediatrician, physiotherapist, nurse etc. who look at options for improving health outcomes at a district level. Incentives will be paid to attract these people. It seems unlikely that a full complement would be available in each district due to work force constraints. SARRAH is providing technical inputs as well as support to the Ministerial Task team leading this initiative, for example a 6 month costed work plan for the MTT. / Indicator 2: Improved performance of key programmes for PHC (Primary Health Care) – increased coverage of basic package of PHC (B) / 2012 Milestone: Basic package for NHI agreed / 2012 Actual: A technical report on the basic package of services was submitted to the NHI Technical Specialist in NDOH in June 2011. / SARRAH played a leading role (financing, logistics, rapporteuring) in an international conference on NHI in late 2011 for 500 delegates which contributed to the ongoing deliberations on the basic package of services (among other aspects of NHI). The current status of deliberations on the basic package is unknown as the department is taking this forward internally. / Indicator 3: Timescale for applications for medicine registration (C) / 2012 Milestone: Staff trained on on-line registration and tracking system (EDMS and CTD) / 2012 Actual: 120 staff were trained in the on-line system but limitations in the NDOH servers and IT system prevented implementation of the new software. Since staff are unable to use the new system they will almost certainly need to be re-trained once the IT challenges have been resolved. Ultimately, the proposed system will allow on-line tracking and management of applications in a secure yet transparent way which is intended to improve throughput. / 2012 Milestone: No further growth of evaluation back-log / 2012 Actual: The evaluation back-log was considered by interviewees to be as bad, if not worse than before the 2010-2011 intervention by SARRAH. A recent Daily News article (30 May 2012)[7] quoted Dr Nicholas Crisp, the SAHPRA Project Leader contracted by HLSP , as saying that the current backlog would take up to five years to clear at the present rate of progress. Pharmaceutical company executives were quoted in the same article saying that they had up to 600 applications at the MCC with some of them having been filed almost four years ago. However, the AR was informed by the NDoH lead that she was currently in the process of hiring consultants (for 6 months) to work on clearing the back log. / As was noted in the previous annual review, releasing critical drugs from this log jam can have enormous economic benefits – a saving of R4.7 billion was achieved partly as a result of the previous backlog project – which helped make cheaper antiretroviral drugs available.[8] However, part of the problem relates to hundreds of applications for relatively unimportant drugs in terms of health outcomes and a system for prioritising applications is needed. Resolving the IT issues and operationalizing the online system, whilst outside the immediate control of SARRAH, is central to improving the throughput of applications and needs to be prioritised. A suite of options for getting the IT system up and running has been provided by SARRAH, but the costing is still to be done. / Indicator 4: SAHPRA (South African Health Products Regulatory Authority) establishment (B) / 2012 Milestone: On-line registration and tracking system (EDMS and CTD) in place. / 2012 Actual: Implementation stalled owing to limitations of the Civitas/NDOH IT system - see indicator 3 above). / 2012 Milestone: Enabling legislation in Parliament. / 2012 Actual: A Cabinet Memo was drafted by HLSP consultants and the proposed legislation has been gazetted for public comment which closed on 12th June. The Minister of Health announced during his budget speech that SAHPRA will be launched as a Schedule 3a Public Entity by 1 April 2013. SARRAH supported the drafting of a business plan for SAHPRA which was a requirement of Treasury. / 2012 Milestone: Draft regulations prepared and consulted with industry. / 2012 Actual: SARRAH inputs speeded up drafting regulations and the consultants assisted in the engagements with industry. / 2012 Milestone: Revised fees operational. / 2012 Actual: The revised fee structure has been discussed with industry and re-submitted to the Minister for approval and should be published by the end of June 2012. However, it seems unlikely that increased fees will be acceptable until the necessary improvement of service is achieved. / Beyond the specific milestones listed above, there are critical negotiations still required between NDOH and Treasury which will draw on the technical assistance provided by SARRAH. Likewise the establishment of SAHPRA has implications for staff which apparently have to be addressed at Ministerial level. This entails job descriptions prepared by NDOH being approved by the Ministry of Public Service and Administration before agreements with organised labour can be finalised. While all these aspects draw on SARRAH contributions, the speed of progress is largely beyond SARRAH’s control. / Indicator 5: Establish Office of Health Standards Compliance (B) / 2012 Milestones: OHSC established and operational. / 2012 Actual: Legislation has been drafted with assistance of HLSP consultants and published for comment which is currently being analysed. SARRAH assisted with collating comments. / Four teams of Inspectors have been trained and are currently refining the audit tools. The more senior inspectors were sent for training with the UK Care Quality Commission. Another four teams are to be established with HLSP support. / The Cluster Manager at NDOH said that without SARRAH support the OHSC could not have made the progress that it has. There were no staff initially but the initial SARRAH inputs work allowed a Director’s position to be filled in February 2011 and there has been a subsequent increase in budget allocation from NDOH in response to the groundwork completed. Thus SARRAH is playing an “invaluable” catalytic role. / 2012 Milestone: 25% of facilities certified / 2012 Actual: Until the legislation is finalised the inspectorate has no legal authority but voluntary evaluations are being carried out. / Recommendations: / SARRAH has undertaken a much broader scope of work than originally anticipated under NHI and this should be captured in the logframe to accurately measure the programme’s performance. / Activities under Output 3 have all been adversely affected by delays to the legislative process which were not anticipated. Regular internal assessment (for example aligned with quarterly reporting) of legislative progress may enable HLSP to better sequence programme inputs (e.g. to delay staff training until legislative mandates are received). Milestones relating to legislative processes could also be updated to reflect more realistic timeframes. / Any future SARRAH support to medicine regulation or supply chain management may benefit from a political economy analysis to identify champions and vested interests which can speed up or slow down reform processes. / The current contract with the SAPHRA service provider (Benguela Health) finishes in July but the DDG Health Product Regulations expressed concern that further support may be required to implement SAHPRA, particularly in the area of labour law. Given that SARRAH currently supports a labour law consultant for SANAC it may be possible to use the same person for this task. / As support begins to wind down, the OHSC work faces similar challenges and there is a need for ongoing support during the implementation phase. There is also further work required on evaluation of the standards. / Impact Weighting (%): 31% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? N
[6] SARRAH, Jan 2012. NHI Briefing Pack: A Resource Document for Managers to Prepare for the District NHI Pilots.
[8] Minister of Health, Budget Speech 2010, http://www.doh.gov.za/show.php?id=1924

Output 4: Strengthen performance management & strategic planning for HIV and health services at national and provincial level
Output 4 score and performance description: A / SARRAH’s ongoing support has focussed on improving asset management, as poor performance in asset management has been the primary contributor to qualified audits. To date, all NDOH sites around the country have been completed and Mpumalanga, Kwazulu-Natal and Eastern Cape provinces are under way. The new asset management system currently being implemented is expected to improve matters and progress will be known once the next Auditor-General’s report becomes available (in June/July 2012). / Work on assessing the competency of public sector hospital and district managers and organisational restructuring supported by SARRAH prior to this review period is being taken forward by the NDoH. A Staff Circular in November 2011 informed all staff that the new organisational structure had been approved by the Department of Public Service and Administration. As of May 2012, 4 of 6 Deputy Director Generals had been appointed. DFID and HLSP understood that slow recruitment is in part due to the right candidates not being available. Despite these challenges, improved HR procedures are in place and NDOH and Provincial structures are being harmonised. The Presidency is promoting the NDOH restructuring as a model process for other departments. The organisational capacity of the Department is critical to South Africa’s ability to drive through the process of health sector reform. / In August 2011 the Government a gazetted a Green Paper, The National Policy on Regulating Management of Hospitals. Positions of hospital CEOs were re-advertised in February 2012, at the time the Minister was quoted as saying ‘"We want to ensure that we have the right people with the right skills and experience in our hospitals."[9], [10] Interviewees reported that a team within NDOH is currently sifting applications, however the Minister is taking a personal interest in Hospital CEO appointments. / Most of the work supported by SARRAH under Output 4 has been carried out by sub-contractors, several of whom were not selected by the implementing agency and much of this work was not carried out within this reporting period. In addition, the sensitive nature of some of the findings and programmes meant that quality assurance and subsequent interventions were largely led by the NDOH. Consequently SARRAH’s internal reporting against this Output is not as current as other Outputs. / In addition to the work above, inputs in this reporting period not specifically reflected by the logframe indicators included providing three consultants seconded to a Technical Support Unit in the NDOH. Two of these consultants were subsequently absorbed by the NDOH. The support provided included assistance with provincial financial management, asset management, conditional grant management and supply chain management. All provinces submitted 2012/13 business plans in March 2012 which were approved in time for the beginning of the new financial year (April).
Progress against expected results: / Indicator 1: Competency of public sector district and hospital managers (A+) / 2012 Milestone: Ministerial Task Team established to implement recommendations / 2012 Actual: SARRAH support to this work stream was completed in Quarter 1, 2011 with the completion of competency assessment of all public sector hospital and district managers carried out by DBSA. Informed by the analysis in this report in August 2011 the Government gazetted a Green Paper, The National Policy on Regulating Management of Hospitals. The aims outlined in the policy are to: ensure implementation of applicable legislation and policies to improve functionality of hospitals; ensure appointment of competent and skilled hospital managers; provide for the development of accountability frameworks; and to ensure training of managers in leadership, management and governance. The paper provides a framework for the classification of hospitals and the job description and competencies of CEOs. Positions of hospital CEOs were re-advertised in February 2012, at the time the Minister was quoted as saying ‘"We want to ensure that we have the right people with the right skills and experience in our hospitals."[11], [12] Interviewees reported that a team within NDOH is currently sifting applications, however the Minister is taking a personal interest in hospital CEO appointments. / Indicator 2: Organisational development of the public health sector (a restructured NDoH National Department of Health) (B) / 2012 Milestone: Recruitment of top structure completed / 2012 Actual: The new NDoH structure has been adopted and approved, including by the Department of Public Service Administration. Staff were formally notified of the new structure in November 2011. All Deputy Director General Positions have been advertised and 4 of the 6 filled. All Chief Director positions have also been advertised. / 2012 Milestone: Lower structures designed and agreed / 2012 Actual: The restructuring of lower levels is being taken forward internally by DDGs as they are appointed. The annual review was informed of a number of staff recruitment processes which are ongoing or complete by interviewees. / 2012 Milestone: Performance management system in place / 2012 Actual: An evidence-based e-appraisal system has been developed and was launched in April 2012. Two templates are used, one for staff below Director and another for Director and above. The manual appraisal system is operating in parallel owing to IT limitations but all appraisals should be on-line by 2013. A new Performance Management Directorate is responsible for taking this forward. / Indicator 3: Service Transformation Plans agreed and monitored through APP (A) / 2012 Milestone: 9 STPs agreed and approved by provincial HoDs and NHC / 2012 Actual: 9 STPs were developed and approved. / Indicator 4: Number of national and provincial DOHs with an Unqualified Audit Opinion (B) / 2012 Milestone: 3 of 10 Provinces receive unqualified audits / 2012 Actual: 2 of 10 Provinces received unqualified audits; the NDoH audit was also qualified. SARRAH support has focussed on improving Asset Management as poor performance in asset management has been the primary contributor to qualified audits. To date, all NDOH sites around the country have been completed and Mpumalanga, Kwazulu-Natal and Eastern Cape provinces are under way. The new asset management system currently being implemented is expected to improve matters and the situation will be known once the next Auditor-General’s report becomes available (June/July 2012). / Recommendations: / Indicators 1, 2 and 3 refer to areas of work in which SARRAH no longer has a direct input, if these indicators are to continue to be reported on a mechanism needs to be developed to enable SARRAH/HLSP to report against progress – for example, updates could be provided by NDOH at SARRAH Steering Committee Meetings. / Impact Weighting (%): 19% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? N
[9] Business Live, 23 Feb 2012. Health minister wants service overhaul. http://www.businesslive.co.za/southafrica/2012/02/23/health-minister-wants-service-overhaul
[10] Health-e, 24 Feb 2012. Hospital CEOs to reapply for jobs. http://www.health-e.org.za/news/easy_print.php?uid=20033447
[11] Business Live, 23 Feb 2012. Health minister wants service overhaul. http://www.businesslive.co.za/southafrica/2012/02/23/health-minister-wants-service-overhaul
[12] Health-e, 24 Feb 2012. Hospital CEOs to reapply for jobs. http://www.health-e.org.za/news/easy_print.php?uid=20033447

Output 5: Strengthen system to effectively monitor and evaluate national and strategic plans for HIV & AIDS and health
Output 5 score and performance description: B / While good progress has been made in producing the new National Strategic Plan for HIV & AIDS, STIs and TB, and this includes proposed indicators which were developed with SARRAH technical assistance, the M&E framework has not yet been developed. The new National Health Information Centre is able to collate information from the District Health Information System, StatsSA (socioeconomic data) and financial data from the NDOH but it remains to be seen how effective this will be for M&E of the various health programmes. / A National M&E Framework for monitoring the NSDA has been developed and SARRAH is represented on the Health Data Advisory and Coordination Committee (HDACC). / In addition to planned activities, there is good buy-in from the Presidency into the SARRAH Impact Evaluation, which will include evaluation of NSDA indicators. The Presidency will host the next Impact Evaluation Steercom in the Presidency and the Deputy President’s office will also participate.
Progress against expected results: / Indicator 1: SANAC (South African National Aids Council) M&E systems strengthened to monitor and evaluate multi-sectoral responses in HIV&AIDS in the public and private sectors (C) / 2012 Milestone: National M&E framework developed and disseminated with PACs, NAC and private sector. / 2012 Actual: The SANAC M&E framework is not yet developed but the reviewers were told that this will be given priority by SANAC once immediate actions related to restructuring are accomplished. However, HLSP provided TA for the development of M&E indicators which were incorporated in the new NSP. / Indicator 2: Joint national monitoring of the NSDA (Negotiated Service Delivery Agreement) (A+) / 2012 Milestone: Joint monitoring (Presidency and NDoH) in place. / 2012 Actual: HLSP contracted the Health Information Systems Program South Africa (HISP) from April 2011 to March 2012 to develop the National Health Information Centre (NHIC) in collaboration with the Strategic Planning Cluster of the NDOH. The NHIC, recently renamed the National Health Information Repository and Data Warehouse (NHIRD), has been established and demonstrations given to the NDOH, other departments and the Presidency. The Centre provides up to date information not only on routine National Indicator/Data Sets (NIDS) but also, among others, District Health Expenditure Review data, Ante-natal Survey data and HCT Campaign data. Thus the Centre is well placed to undertake monitoring of the NSDA. / Following the production of a National M&E Framework funded by SARRAH, which details how the NSDA should be monitored, the Director General set up a Health Data Advisory and Coordinating Committee (HDACC) which reviewed the framework document and is responsible for taking the work forward. The DFID Senior Health Advisor sits on this committee and the Minister of Health launched the first HDACC report in November 2011. / There is good buy-in from the Presidency into the SARRAH Impact Evaluation which will include evaluation of NSDA indicators. The Presidency will host the next Impact Evaluation Steering Committee in the Presidency and the Deputy President’s office will also participate. / 2012 Milestone: First review produced / 2012 Actual: First HDACC report was launched November 2011 and published in February 2012.[13] / Recommendations: Given the critical importance of effective M&E for managing the health system, SARRAH should continue its support of SANAC and HDACC to help ensure that the necessary data is made available and effectively used. / Impact Weighting (%): 10% / Revised since last Annual Review? N / Risk: Low/Medium/High / Revised since last Annual Review? N
[13] NDOH, 2012. Health Data Advisory and Co-ordination Committee report. 54pp. Pretoria: NDoH. http://www.doh.gov.za/docs/reports/2012/hdaccreport.pdf

## Section B: Results and Value for Money.

1. Progress and results
Has the logframe been updated since last review? Yes / There was extensive discussion of the logframe during the first Annual Review and subsequently the SARRAH team made further revisions culminating in the current logframe produced 13 July 2011. The changes were primarily made to accommodate changes in strategic direction requested by the Director General (see 2011 Annual Review) and refinement of milestones to better reflect the envisaged activities. / 1.2 Overall Output Score and Description: A / 1.3 Direct feedback from beneficiaries / For the purposes of this review the beneficiaries are considered to be the government officials working in the National Department of Health, staff and members of South African National Aids Council, staff of the Treatment Action Campaign and members of the Parliamentary Oversight Committee. / Beneficiaries were, without exception, highly positive about the inputs made by the SARRAH programme for supporting aspects of health reform; / Specifically, beneficiaries commented on high quality technical support provided in rapid time; / More than one beneficiary citied SARRAH’s input as enabling them to move forward from a ‘standing start’ for example, one Cluster Manager described how DFID support for an additional Director’s post had allowed work to be done that laid the groundwork for a significant expansion of the department. This work was catalytic and enabled the department to argue successfully for an increased budget allocation the following year; / A number of beneficiaries citied SARRAH’s flexibility as a critical benefit; / Representatives of TAC and SANAC also commented on how SARRAH’s continued support had enabled them to implement change processes at a time when other donors were unwilling or unable to provide the support needed; / One beneficiary commented that they would prefer a more systematised approach to partnership, i.e. around a clearer programme of outputs; / One beneficiary commented that relationships with SARRAH had been more difficult as funding for significant work was ending; / Where for example, consultants inputs were not up to scratch, beneficiaries were happy with the response from SARRAH in addressing this.

1.4 Summary of overall progress / Progress has been recorded above for each indicator. Overall, 57% of Jan 2012 milestones have been reached. Overall, where milestones have not been met this is largely the result of initial unrealistic expectation when setting milestones in partnership with the programme partners. For example, milestones that relate to legislative progress have not been met. There is no doubt that SARRAH is supporting institution building and strengthening which is critical to the transformation of the South African health system and meeting the goals of this programme. SARRAH is facilitating broad consultation and policy debate on the implementation of the National Health Insurance. Given the continued political commitment to transform the health sector is seems reasonable to expect that legislative delays which have slowed SARRAH’s progress in some areas will be overcome. However, ensuring that institution building translates into health outcomes will require organisational and human capacity development both within the NDOH and throughout the provincial and district health systems. While capacity building is ongoing at most levels of the health system, according to interviewees, further technical assistance is going to be needed for the short to medium term to assist the establishment of institutions.
1.5 Key challenges / SARRAH financial support: due to frontloading, SARRAH financial resources will be fully utilised at the end of this year. It is considered that continued SARRAH support (due to a level of flexibility not provided by other donors) is critical to enabling TAC to fully implement change processes which are underway. Similarly continued support to SANAC would facilitate the dynamic change underway at this organisation (although SANAC has a core operating budget and should be able to secure funding from other donors more easily). With regard to SAHPRA and OHSC, SARRAH support has laid strong institutional foundations, however, once legislative delays are overcome additional technical assistance could assist these institutions get off to a strong start. / Organisational and human capacity: South Africa is implementing an incredibly ambitious reform of the health sector, the goal of which is for all South Africans to realise a long and healthy life. SARRAH support has in large part contributed to the institutional framework which will govern South Africa’s reinvigorated response to HIV and AIDS and the health system more broadly. Ensuring that South African has the human and organisational capacity to implement these institutional frameworks is critical to realising the vision for long and healthy lives. SARRAH’s approach to capacity building is therefore critical. At Ministry level SARRAH currently fills a gap in terms of the supply of technical knowledge, both in terms of supplying evidence and advice and in commissioning it through the drafting of Terms of Reference and identification of consultants. There is a hypothetical risk that by filling gaps weaknesses may be sustained which might otherwise be addressed. / Political will: the vision and energy which Minister Motsoaledi is bringing to the health sector transformation process was considered by interviewees to be unique. There is such a broad base of support for health sector reform that a change in Minister (ANC National Conference at the end of 2012) would not throw the reform process of track, however, an appointment of a new Minister could result in a significant change of pace.
1.6 Annual Outcome Assessment / The expected outcome is ‘improved governance of an integrated, effective response to HIV&AIDS and health in South Africa’. Excellent progress has been achieved against achievement of January 2012 milestones, with 3 fully achieved and 1 partly achieved. No data is available against the remaining indicator. / Indicator 1: UNGASS national composite policy index / The 2012 Milestone of publishing the National Strategic Plan for HIV& AIDS, STIs and TB (2012-2016) was achieved by SANAC with SARRAH support, which included contributions to the review of the previous NSP (2007-2011) which were part of the process. The other milestone for this indicator was to have a functional Multisectoral M&E system in place but this has not yet been achieved. However, SANAC will be prioritising this process once its restructuring is complete. In the meantime, there is close involvement of the Presidency in the Impact Assessment of SARRAH which will contribute to better coordination of M&E across sectors. / Indicator 2: % of fully immunized children <1year / The 2012 Milestone was >95% and this has been achieved with the actual figure being 95.2% (DHIS 2011/12). / Indicator 3: number of new patients (adults and children) initiated on ARVs / The 2012 Milestone for the number of new patients (adults and children) initiated on ARVs was 545,000; the latest available estimate exceeded this target by nearly 12% at 617,147 (DHIS 2011/12). / Indicator 4: percentage cases treated successfully out of all estimated TB cases (all forms of disease) for a given period / The 2012 milestone for the percentage of TB cases treated successfully was 75% but current data is not yet available as the TB Cluster is still finalising the data. / Indicator 5: improved donor coordination and harmonisation / The 2012 Milestone for an Aid Effectiveness planning forum to be functional has been achieved with technical support provided by SARRAH, which was “highly appreciated by the Minister”. Meetings between the Minister and Heads of Missions take place annually and the DG and Technical Heads of missions meet bi-annually. Donor coordination and harmonisation was said to have improved. / Assessment of Theory of Change / The original Project Memorandum does not include a theory of change and in spite of the diversity of activities undertaken by the SARRAH programme, a common overall purpose is evident and all the activities seek to make the South African health system more effective, more equitable, more accountable and more transparent, all of which should ultimately lead to a healthier, less HIV and AIDS stricken and more productive society. This vision is captured in the NSDA, which SARRAH was designed to support. The team that is currently designing a full Impact Assessment (IA) of SARRAH concluded in its Inception Report that although “a common, overarching framework is crucial to carrying out an IA mindful of the overall context that underpins the programme, the work-streams should be first considered individually before an attempt is made to aggregate their overall impact on the South Africa health sector.” / The IA team undertook a thorough, consultative and participatory exercise to understand in detail what the activities conducted as part of the SARRAH programme consist of, what they seek to achieve and through which means. It became clear that the log-frame in its current form is not an appropriate conceptual framework within which the IA could be undertaken: it does not capture sufficiently systematically and logically the causal relationship between outputs, outcomes and impacts which will constitute the backbone of the IA implementation phase. However the logframe remains a useful monitoring tool through which valuable indicator data can be collected at regular intervals, and which will inform key parts of the IA.

2. Costs and timescale
2.1 Is the project on-track against financial forecasts: Y/N / Table 1 below shows SARRAH planned and billed expenditure as of March 2012. In agreement with DFID, SARRAH financing has been frontloaded and the all funds will be spent as of December 2012. Thus the programme timescale is ahead of the original schedule. / Table 1: / Summary to date: / Total value of invoices to 31 March 2011 £14,362,378.94 / On-going milestones, work in progress £3,626,421.27 / Total contracted milestones £18,056,853.67 / Committed funds not contracted: £2,175,882.60 / Available Funds £119,479.44 / Total Contract Value to Date £20,352,215.06 / 2.2 Key cost drivers / The main cost driver of the SARRAH programme is technical assistance, including sub-consultants and sub-contractors. In order to ensure that the rates for the technical assistance days are kept as low as possible, HLSP have a Consultancy Services Team, based in the UK, whose role is to procure consultants at competitive rates. A programme record of negotiation results is kept, and this shows that an average savings of 20% was achieved in negotiations since the SARRAH programme’s inception and 84% of the rates have been negotiated downwards. Rates paid to consultants generally average between 40 - 50% lower than the Department of Public Service and Administration’s published upper level tariffs. / The total cost of the Project Management Office (PMO) is budgeted at £4,120,612, which represents 20.2 % of the total programme budget of £ 20 352 000. However the PMO is not just administrative, it includes Technical Leads, and Quality Assurance functions, all of which provide technical assistance to the Partners as part of their role. The Back Office function costs are approximately / £ 1.95 million, which comprises 9.6% of the total programme budget, falling within the 10% indicator generally used to judge efficiency of administrative functions. / 2.3 Is the project on-track against original timescale: Y / SARRAH project funds have been frontloaded (see 2.1 above). Section 1 shows the achievements against planned milestones, overall SARRAH activities are on track, with some delays largely due to legislative processes beyond the project’s control. SARRAH has supported a large number of activities, particularly in support of the National Health Insurance, which are not well reflected in the milestones. In summary, the project is, through prior agreement with DFID, ahead of schedule.

3. Evidence and Evaluation
3.1 Assess any changes in evidence and implications for the project & 3.2 Where an evaluation is planned what progress has been made? / An independent Impact Assessment (IA) has been commissioned by DFID and is being undertaken by Coffey International Development, UK, and the Human Sciences Research Council, South Africa. The SARRAH outputs are very diverse and operate in a complex system of decision making that makes attribution of benefits to any particular action very challenging. The Impact Assessment has made considerable efforts to develop theory of change models with the HLSP Technical Leads for each workstream and has produced an overall TOC model (see Inception Report Impact Assessment on SARRAH, November 2011, p.5) that demonstrates how SARRAH interacts with NDOH, SANAC, TAC and other stakeholders through its many workstreams to ultimately contribute to the NSDA. / An Inception Report which explored the Theory of Change in detail was produced in November 2011. Subsequently, an Assessment Strategy Workshop was held in Feb 2012 and methodologies for the Impact Assessment developed and submitted to DFID in an Evaluation Strategy Report in April 2012. The proposed methodologies are currently undergoing peer review. The proposed IA will take place in 2012 and 2014 with some continuous data collection in between. / Although this model and the workstream TOCs are plausible, some of the causal linkages to high level outcomes and impacts (e.g. greater and more equitable access to health services) are remote, especially as the total SARRAH budget represents only about 0.2% of South Africa’s annual health budget. This is not to say that the interventions are ineffective but, as noted above, are often catalytic in their effect and intermediate outcomes must be considered as evidence of programme success.

4. Risk
4.1 Output Risk Rating: Low/Medium/High check aries / 4.2 Assessment of the risk level / HLSP maintains a comprehensive risk analysis table, which also lays out mitigating actions. The assessment of risk remains current and no additional risks were identified. However, recommendations in this report in relation to logframe inputs and outcomes (risks D and E) and recommendations in the VFM report regarding Terms of Reference (Risk C) need to be implemented to ensure that mitigation strategies are being implemented.
Risk of funds not being used as intended / All SARRAH funds are managed by HLSP on a milestone matrix basis for programme funds allocation, billing and programming. The recent value for money audit concluded that the milestone matrix is an effective and reliable method of billing and accounting for programme deliverables, and for monitoring project progress (albeit at a high level). The audit found the following benefits for DFID: / reducing administrative and transaction costs / knowing the cash flow well in advance / simplifying the process of approving payments / restricting exposure to cost overruns and exchange rate fluctuations / 4.4 Climate and Environment Risk / SARRAH is supporting the strengthening of South Africa’s national health system. A stronger health system will lead to environmental benefits through, for example, a healthier population being more able to care for the environment and better management of hazardous substances. It will strengthen South Africa’s capacity to mitigate the impacts of changing disease burden brought about by a warmer climate, for example an increase in malaria. / HLSP operations ensure that carbon miles are recorded in expenses claims. Office paper is recycled.

5. Value for Money
Guidance on completing the Value for Money (VfM) section of the Annual Review indicates referral to the VfM measures set out in the business case. SARRAH was designed prior to the business case era and as a result no tangible references are made to VfM in the original Programme Memorandum (PM). However, this section of the report draws on the SARRAH value for money audit, which was completed in January 2012[14]. The VfM report emphasises economy aspects of VFM. The ongoing impact assessment will enable more robust future assessments of efficiency and effectiveness aspects of VfM. / 5.1 Performance on VfM measures / The PM sets out the costs of the programme to be £ 25 million over five years. Costs are disaggregated by all programme outputs, over a period of 6 years. No detail of the costing of each of the outputs is presented. The Economic Appraisal section of the PM is hinged on the cited fact that HIV and AIDS slows economic growth in South Africa by 0.5% each year, which amounts to a loss of £100 million annually. There is no reference provided for this evidence. It is argued that the “economic rationale for SARRAH … is to reduce the negative effect that HIV AIDS has on the macro and micro-economy.” / DFID South Africa commissioned a VfM Report in November 2011 to respond to DFID’s new requirements, the review approached VfM by addressing four weighted questions: / Are programme procurement and execution processes strong and in order so that input to output conversion is done efficiently? (15%) / Are the deliverables fit for purpose? (30%) / Are the deliverables produced at fair and reasonable cost? (20%) / Are the deliverables effective-being utilized and having the intended impact? (35%) / The set of questions is on a par with DFID’s 3-E framework, in that question 3 is linked to Economy, question 1 to Efficiency and Questions 2 and 4 to Effectiveness. Answers were scored between 0 and 4 where 0 is low and 4 high. Scores were converted into percentages, 4 being 100%. / Value for Money was measured for a sample of 26 of 173 projects commissioned to date. This represents 69% of total project expenditure and 19% of the total number of projects. However one of the programme’s outputs (the TAC Grant) was not evaluated for Value for Money, because it did not lend itself to the above presented assessment. This presents a significant caveat to the VfM analysis. / VfM Performance / The overall VfM score of the programme was found to be 80.65%, which translates as overall good value for money. To note is that the programme’s average was brought down by answers to questions 1 and 2, which respectively scored 75.39 and 75.66%. / Q3- Are deliverables produced at fair and reasonable cost? (Economy) / In order to answer this question, assessors were asked to rate the charge in relation to the deliverable produced on a scale of 0 to 4. One assignment scored 0 and two scored 2, and all the others scored 2.5 and above. The report makes no recommendations regarding costs, which seemingly means that procurement and costs are being appropriately dealt with. The report also states that assessments were made on the basis of professional expertise, and that justification and evidence had to be supplied for the rating. It thus seems that the Economy aspect of VfM was fulfilled. / Q1- Are programme procurement and execution processes strong and in order so that input to output conversion is done efficiently? (Efficiency) / This question was answered by asking 19 sub-questions related to 3 areas: terms of reference, procurement and its economy, and on time and efficient delivery of output. The sample scores most poorly on the last point, efficient delivery of output: 64.1%. Given that this is key to Efficiency, it may be one to monitor and evaluate closely in the future. Further, it is not clear that the way in which the efficiency of input-output conversion is scored is adequate. Indeed, questions are possibly overly focused on start and completion dates and work plans, and not enough on how inputs are converted into operational outputs. / Q2- Are deliverables fit for purpose? (Effectiveness) / This question is answered by asking 9 questions, linked to three areas: whether or not the final report/product contains certain specifics such as findings, methodology, gender assessment etc, whether DFID and the client formally accept the key deliverable without reservation and whether there is evidence that other key beneficiaries are satisfied with the deliverable. / It is noted in the report that the criteria on user satisfaction were not looked into despite it arguably being the most important. The check was not undertaken ‘as it would require significant input from beneficiaries’ which was not scheduled in this VfM assessment. This is an unsatisfactory situation which will need to be improved in the next assessment. / Q4- Are deliverables effective, being utilized and having the intended impact? (Effectiveness) / The VfM report states that there were restrictions in interviewing stakeholders and beneficiaries, which impacted on being able to inspect evidence of utilisation. The scores for question 4 were thus based on interviews with team leaders who cited anecdotal evidence. The VfM report recommends interviewing beneficiaries and inspecting utilisation, performance and sustainability of deliverables in the next VfM report. This is a potentially serious caveat to the VfM measure. / 5.2. Commercial Improvement and Value for Money / The VfM report states that ‘the mechanics of the accounting and recording with the Milestone Matrix appears robust and the information reflected is accurate and reliable’. / 5.3. Role of Project Partners / The implementing partner and its consultants are held in high regard by the beneficiaries who frequently refer to SARRAH’s ability to deliver quality products quickly. Section 2.2 shows that rates paid to consultants generally average between 40 - 50% lower than the Department of Public Service Administration’s published upper level tariffs. / Normally the selection of consultants and issuing of contracts is the responsibility of HLSP, who then assume risk on the consultants’ performance. However, there have been a substantial number of instances where NDOH have taken responsibility for the appointment of consultants, and instructed DFID and HLSP accordingly. Twelve such cases occur in the sample of 23, mostly the higher value contracts. Most of these cases required the sub-contractor to report directly to NDOH, with HLSP not being able to fulfil their normal monitoring, supervision, and quality assurance role, and being unsighted on the final deliverables. These are responsibilities which are central to the HLSP contract with DFID. As an aside, the standard of the terms of reference for all these activities were assessed as being ‘below par’. / Fortunately in 8 out of 12 cases these prescriptive appointments did not adversely impact, to any significant extent, the scores received, and deliverables were eventually produced to a quality and standard that satisfied client (according to letters from the client confirming this). However, there were four cases where the result of the activity was unsatisfactory with resultant poor value for money, scoring an average of 41% for the four assignments, with the worst being 13%. / In all twelve cases senior management input from HLSP was unduly high, as they had to take extra ordinary measures to fulfil their due diligence obligations, and respond to various ‘situations and dynamics’ emanating from the extra ordinary reporting relationships (Subcontractor to NDOH). Steps have however been instituted which come into play whenever the Department appoints the Consultant. / 5.4 Does the project still represent Value for Money: Y / According to the methodology used in the VfM report commissioned in January 2012, the project represents good value for money, with a score of 80.65%. However, the report makes clear that question 4 (effectiveness), was not comprehensively covered due to beneficiary data not being looked into. Furthermore, measures of efficiency were also lacking in substance as explained in section 5.1. On the Economy front, though the programme scored well. One of the programme outputs, the TAC grant, was not evaluated on value for money, due to ‘it not lending itself to being scored by the assessment tool’. It is however noted that £913 787 had been spent up to the end of October 2011, and that in its first year 2010 TAC ‘were somewhat disorganised, and there was little visibility or clarity on what they were doing or achieving. However, TAC has undergone a major restructuring in the recent past and received a positive audit in September 2011. Both its financial and general M&E systems have undergone substantial re-alignment in accordance with a modified mandate. / 5.5. If not, what action will you take? / In order to ascertain whether the programme is good value for money, future VfM reports would need to focus more on the efficiency and effectiveness facets of value for money. Indeed, in this case they were either ill-measured, or not measured at all due to constraints arising from the nature of the intervention. These constraints are considerable and relate primarily to the complex causal relationships described in the theory of change elsewhere in this review. The current impact evaluation will assist in future assessment of effectiveness elements of VfM.
[14] Value for Money Review of the SARRAH Programme, DFID South Africa, November 2011 – January 2012

6. Conditionality
6.1 Update on specific conditions / Not applicable

7. Conclusions and actions
SARRAH is delivering highly valued and high quality inputs to the Government’s health transformation programme. The support has an exceptionally high level of ownership within the National Department of Health (especially by the Director General) and is clearly aligned behind and contributing to the NDoH 10-Point Health Plan (see Fig. 1). / SARRAH support has enabled the NDoH to respond rapidly to new energy behind South Africa’s health sector transformation since the appointment of Minister Motsoaledi in 2010. In particular it has made technical inputs to building institutions such as National Health Insurance, and medicine and facility regulation and monitoring. It has supported organisational reform within the NDoH and laid the groundwork for the recruitment of appropriately skilled hospital CEOs. SARRAH’s support in the past year has been focused on the National Health Insurance. Interventions in support of NHI are laying the foundation for better quality healthcare across the country, regardless of the eventual outcome of the NHI policy debate. The Minister was quoted in February 2012 as saying, “When we launched the NHI Green Paper, we said a precondition for the NHI to survive and be successful is that the quality of healthcare in public institutions has to improve. It is non-negotiable that we overhaul and improve quality.”12 SARRAH is providing critical support to this process. / An effective health system requires monitoring and accountability and SARRAH’s core support to TAC and SANAC has been a key facilitator in enabling these two bodies to weather a period of loss of identity, purpose and in SANAC’s case, leadership. Both are now well on the way to fulfilling their core role in monitoring the national strategic plan and holding government to account. / The responsive and flexible nature of SARRAH’s support is praised by partners. However, the strong level of ownership brings with it challenges for programme management. In particular SARRAH’s full complement of work and progress is not reflected in the logframe. And where financial support for activities has ceased SARRAH reporting does not always continue to monitor progress. / Recommendations for remaining 6 months / Milestones relating to legislative processes should be revised so that future AR / PCR are able to score against a more realistic timeframe (see below recommendations for further possible amendments to the logframe) / SARRAH addresses significant gender related aspects of healthcare, however, gender aspects of the programme need to be better reflected in project reporting / Mechanisms for reporting on progress of interventions for which SARRAH is no longer providing financial support should be identified. These could include updates from NDoH at SARRAH steering committee meetings and inclusion in quarterly reports of media reporting against these interventions. / Increase the number of case studies on SARRAH’s website. / SARRAH’s approach to capacity building should be reflected in all new ToRs and appropriate skills for capacity building should be a prerequisite in recruiting consultants. / New DFID Development Policy Committee paper on Capacity Development should be shared with HLSP. / DFID should consider supporting systematic documentation of South Africa’s response to the HIV and AIDS crisis in order to capture lessons learned to inform both South Africa’s health sector transformation and development of other health systems in the region. Support through the second window of the DELPHE programme (support to Higher Education Institutions, currently under tender) would enable a South African Higher Education Institution to lead this process. The Emerging Powers Team also have a source of finance (Global Partnerships Programme) which supports projects in emerging powers which have regional benefit. / Recommendations for further financing / Further support to TAC is critical to supporting organisational restructuring and implementation of their new business plan / Further support to SANAC and Parliament would support establishment of necessary oversight of the process of health reform / Additional support to SAHPRA and OHSC, when legislation is passed, could support effective functioning of these institutions / SARRAH is providing high quality technical inputs to the NHI policy debate and enabling broad stakeholder consultation, continuing this support would capitalise upon the current momentum behind health service reform / Recommendations if further funds are committed / Logframe should be revised to tighten up outputs and outcome level indicators / Legislative indicators should be removed as these are outside the control of the project / Small amendments to Output language would increase clarity / New gender indicators should be included – TAC indicators are not reflective of TAC’s core work / Milestones should reflect more realistic timeframes / Indicators and milestones could better reflect to totality of SARRAH’s interventions, in some cases fewer indicators may assist this / Some Output 1 indicators are more appropriate Outcome level indicators / DFID should consider whether the nature of partnership with the NDoH should form part of the ToC to capture benefits of this approach / Any future support to medicines regulation or supply chain management would benefit from political economy analysis (DFID has experience in Mozambique and Burundi) / Quarterly management assessments of the progress of legislative or policy processes may assist in sequencing of future interventions / Capacity Building and Organisational Capacity of NDoH: Strategies to strengthen the approach to capacity building could include consider more use of secondments (in and out), twinning and mentoring. A recent multi-donor evaluation of Public Sector Reform identifies good experience with organisational capacity building (Ugandan Ministry of Finance or Indonesia’s External Audit Board) review of this may identify lessons for SARRAH / Request support from the Results Hub in DFID’s Politics State and Society Team in measuring governance results and measures of VFM / Where NDoH is the lead in identifying consultants, national systems of procurement should be utilised

8. Review Process
The second Annual Review of the SARRAH programme took place between 28 May and 1 June and was carried out by Zoë Wildig, Governance Adviser, DFID London, and Prof John Seager, a Freelance Public Health and Development Consultant contracted by Coffey International Development, London. / The Reviewers were briefed by the Senior Health Adviser and Health Team Programme Manager, DFID SA, and then by the SARRAH Programme Manager of HLSP. Technical Leads in the implementing agency were interviewed and various SARRAH, NDoH and other government documents were consulted. Senior representatives of the three partners (beneficiaries), namely NDoH, SANAC and TAC were also interviewed. The interviews were conducted in Pretoria and Cape Town, the majority face-to-face but some via teleconference. Details of interviewees are provided in Appendix 1.