PROJECT TITLE	DEVELOPMENT OF NATIONAL STATISTICAL SYSTEM IN KENYA (NSS)
GOAL	Indicator	Baseline ( 2004)r		Milestone1 (2007)		Milestone 2 (2009)		Target (2011)	Government remains committed to poverty reduction. / Donors remain committed to supporting Government’s efforts. / KNBS/NSS information is used to inform and direct pro-poor policies and programmes and leads to improvements in selected Vision 2030 and MDG indicators as a result of better policies/programmes. / The 2009 Census has important uses for future planning, policy making and electoral reform processes; i.e. resource allocation; boundary review and constituency delineation.
Improved use of statistics and information contributes to sustainable poverty reduction in Kenya through more effective design, implementation and monitoring of policies and programmes.	Annual growth rate of GDP(%) (at constant prices)	5.1		7.1		8.3		9.1
		Source
		KNBS Quarterly National Accounts statistical release / Vision 2030 National Reporting Framework
	Indicator	Baseline (2004)		Milestone 1 (2007/8)		Milestone (2009/10)		Target (2010/11)r
	Population growth rate (%)	2.8		2.7		2.6		2.5

		KNBS annual population projections; 2009 Census / Vision 2030 National Reporting Framework
	Indicator	Baseline (2006)		Milestone 1		Milestone 2		Target (2011)r
	Population below the poverty line (%)	46					33
		Source
		KNBS Integrated Household Budget Surveys. Annual estimates from KIPPRA / Vision 2030 National Reporting Framework
	Indicator	Baseline (2004)	Milestone 1 2007)		Milestone 2 (2009)		Target (2011)
	Under 5 mortality – deaths per 1000 live births	115	92		74		45
		Source
		Kenya Demographic Health Surveys / Vision 2030 National Reporting Framework
	Indicator	Baseline (2003)	Milestone 1 (2007)		Milestone 2 (2009)		Target (2011)
	HIV/AIDs prevalence in people aged 15-49 (%)	6.7	7.4		6.4		6.3
		Source
		Kenya Aids Indicator Surveys / Vision 2030 National Reporting Framework

PURPOSE	Indicator	Baseline (2004)		Milestone 1 (2007)		Milestone 2 (2009)		Target (2011)	Assumptions
To build a strong NSS by successfully implementing the Statistics Strategic Plan	Staff on terms and conditions of KNBS (%)( from CBS terms)	0%		60%		90%		100%	Government is committed to transparent and accountable decision-making processes. / Implementing the Statistics Strategic plan will contribute to the goal / Increased capacity within Government to provide analysis and evidence to inform pro-poor policy development and monitoring / 1. In poverty, population, health, and economic statistics: national accounts, Consumer Price Inflation. / * Demographic Health Survey
		Source
		KNBS Strategic Plab 2004-2007
	Indicator	Baseline (2004)		Milestone 1 (2007)		Milestone 2 (2009)		Target (2011)
	KNBS website is the key source for dissemination of KNBS and other NSS statistics	Poorly functioning website. Hard copy publication the normal means of dissemination on request		KNBS branded website implemented with limited data		Key statistical data and institutional information on website		An integrated information system implemented covering all sectors
		Source
		KNBS Strategic Plan 2004-2007
	Indicator	Baseline (2004)	Milestone 1 (2007)		Milestone 2 (2009)		Target (2011)
	Production of key statistical surveys & activities	Up-to-date data needed on poverty , child & maternal mortality, HIV/AIDS, population & key economic aggregates	Publish poverty survey results. / Complete data collection for HIV/AIDs survey. Plan for census and DHS*		Full results of HIV/AIDS study published. Publish full results of DHS. Undertake population census & produce preliminary results		Census analysis released. / Revised CPI methodology and data. / Rebased National Accounts. / Complete register of business est,. SME survey, Census of Production
		Source
		KNBS statistical releases 1
INPUTS (£)	DFID (£)	Govt (£)		Other (£)		Total (£)		DFID SHARE (%)
	£6,500,000	???		WB: $20m
INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Indicator	Baseline (2004)		Milestone 1 (2005)		Milestone 2 (2006)		Target (2011)	Assumptions
A strengthened NSS with a coherent institutional framework	Legal framework underpinning NSS	Draft Statistics Bill approved by cabinet – establishing a semi-independent NSO and board		Bill approved by Parliament and placed on statute book		2006 Statistics Act enacted. KNBS established.		Detailed regulations to support the implementation of the Act published, and evidence of these being adhered to	Parliament passes Statistics Act without major amendments. / Effective co-operation between CBS, line ministries and the districts.
		Source
		GoK statute book. / Rebranding of KNBS
	Indicator	Baseline (2004)		Milestone 1 (2005)		Milestone 2 (2006)		Target (2011)
	Effective establishment of the new Board of Directors	New governance structure for semi-independent KNBS outlined in Bill		Board members and function enshrined in law		Board members appointed		Board shows evidence of exercising powers vested in it by the Act
		Source
		The Statistics Act, 2006 No.4 of 2006 Part II, Section 6
IMPACT WEIGHTING	Indicator	Baseline + year		Milestone 1		Milestone 2		Target + year

		Source					RISK RATING

INPUTS (£)	DFID (£)	Govt (£)		Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 2	Indicator	Baseline (2004)	Milestone 1 (2006)	Milestone 2 (2007)	Target (2009)	Assumptions
Statistical infrastructure developed and made operational	Guidelines on concepts, definitions and methodologies produced and applied	Out-of date documentation underpinning statistical methodology , concepts and terms. Little standardisation in use	New draft guidance produced and discussed with Board	Final guidance published and placed on KNBS website	Evidence of terms / definitions and methodologies being put into practice in statistical surveys and activities	CBS and other statistical units are able to use resources effectively. / CBS able to effectively play a leadership role across the NSS following Statistics Act implementation. / National Sample Survey and Evaluation Programme (NASSEP) is used as a sampling frame to all household based surveys.
		Source
		KNBS. Monthly Board meetings . KNBS website
	Indicator	Baseline (2004)r	Milestone 1 (2005)	Milestone 2 (2007)	Target (2011)r
	Updated Central Business Register	Outdated business register (important for economic surveys& national accounts)	Data collection and entry of questionnaire	Comprehensive business register finalised	Business register used for business surveys and economic accounts
		Source
		KNBS. Monthly Board meetings. KNBS website
IMPACT WEIGHTING	Indicator	Baseline(2008)	Milestone 1 (2009)	Milestone 2 (2010)	Target 2011)
	Updated NASSEP	Old frame (based on 2002 data)	Census provides master file of households		NASSEP V
		Source				RISK RATING
		KNBS
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Indicator	Baseline (2004)		Milestone 1 (2005)		Milestone 2 (2008)		Target (2011)	Assumptions
A wide range of high quality statistics outputs delivered. GoK documents produced that include NSS outputs	Vision 2030 Monitoring Framwork populated with NSS outputs	Draft national monitoring framework (NMF) adopted with specified indicators		NMFindicator baseline, milestones and targets agreed by GoK		Monitoring against indicators in NMF begins		Increased range & quality of statistics in the Vision 2030 Annual Reports. / Reference to KNBS/NSS statistics in GOK’s sector plans	Effective user consultation feeds into the NSS work plans / GoK desire to move towards evidence-based decision making. / NSS is producing user-focused and relevant statistical outputs
		Source
		Annual Progress report on Implementation of Medium Term Plan (2008-2012) , Kenya Vision 2030
	Indicator	Baseline (2004)		Milestone 1 (2005)		Milestone 2 (2007)		Target (2011)
	Kenya data included in IMF General Data Dissemination System	GDDS action plan		Data and metadata prepared & verified. Complies with GDDS standards		IMF publishes GDDS including Kenya’s key economic and social data		GDDS regularly updated with data.
		Source
		IMF website
	Indicator	Baseline (2008)	Milestone 1		Milestone 2		Target (2011)
	Number of main KNBS publications broken down by sex	4					8
		Source
		Includes: Census; Demographic Health Survey, Aid Indicator Survey, Household budget survey
IMPACT WEIGHTING	Indicator	Baseline(2008)		Milestone 1(2009)		Milestone 2(2010)		Target (2011))
	Implementation of Census 2009	Main operational and logistical census planning completed. No comms/publicity strategy & RA, particularly dealing with the tribe issue		Comms strategy & risk analysis done. Credible census takes place with no strife.		Publication of preliminary results (less than 1 year after Census date). Results regarded reliable.		Detailed analytical census reports, and full documentation available.
		Source							RISK RATING
		UNFPA Development Partner Forum on Census / KNBS
INPUTS (£)	DFID (£)	Govt (£)		Other (£)		Total (£)		DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 4	Indicator	Baseline (2004)	Milestone 1 (2005)	Milestone 2	Target (2007)	Assumptions
Improved demand for NSS outputs.	Chronic Poverty Research Centre (CPRC) established producing policy relevant analysis	No research organisation that focuses on chronic poverty	Establishment of the CPRC	Chronic poverty issues incorporated in GoK policies & programmes	Increased awareness and use of chronic poverty data in NGO/CSO strategies and action plans by mid 2007	GoK remains committed towards increasing range of data on poverty, and to an effective partnership with CPRC.
		Source

	Indicator	Baseline (2004)	Milestone 1(2004)	Milestone 2(2004)	Target (2005)
	.A basket fund for the KIHBS established providing effective release & monitoring of funds	No mechanism for pooled donor funding of KIHBS	Recruit a financial management agent for funds	Other donors sign up to and support the principles of the basket fund	Funding mechanism operational for KIHBS
		Source
		Contract documents. Common financial and management reports
IMPACT WEIGHTING	Indicator	Baseline (2009)	Milestone 1	Milestone 2	Target (2011)
	Improved capacity to deliver Strategic Plan 2008-12 (as measured by the number of strategic objectives implemented)	0 of 6 objectives met			4 of 6 objectives met
		Source				RISK RATING
		Source: Strategic Plan 2008-2012 (M&E framework) / World Bank mid-term and annual reviews / DFID/WB secondee
INPUTS (£)	DFID (£)	Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

## Activities Log

OUTPUT 1	ACTIVITY 1.1	Milestone 1	Milestone 2	Milestone 3	Risks	Monitoring Officer

	ACTIVITY 1.2	Milestone 1	Milestone 2	Milestone 3		Monitoring Officer

	ACTIVITY 1.3	Milestone 1	Milestone 2	Milestone 3		Monitoring Officer

OUTPUT 2	ACTIVITY 2.1	Milestone 1	Milestone 2	Milestone 3	Risks	Monitoring Officer

	ACTIVITY 2.2	Milestone 1	Milestone 2	Milestone 3		Monitoring Officer

	ACTIVITY 2.3	Milestone 1	Milestone 2	Milestone 3		Monitoring Officer

OUTPUT 3	ACTIVITY 3.1	Milestone 1	Milestone 2	Milestone 3	Risks	Monitoring Officer

	ACTIVITY 3.2	Milestone 1	Milestone 2	Milestone 3		Monitoring Officer

	ACTIVITY 3.3	Milestone 1	Milestone 2	Milestone 3		Monitoring Officer