ADDENDUM TO BUSINESS CASE FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Project Name	Urban Partnership for Poverty Reduction
Country or region targeted	Bangladesh
Type of cost extension	Financing for Scale up
Original project budget	£64.7 million
Original project start and end dates	March 2008 - August 2014
Cost extension value	£3 million
New project end date	March 2015
Business Case Quest Document No.	1248842

INFORMATION
What is the project’s purpose?
Livelihoods and living conditions of 3 million poor and extremely poor people living in urban areas, especially women and children, sustainably improved.
What is the objective of the cost extension?
The objective of the UPPR cost extension is to scale-up the project’s phase-out activities to enhance their sustainability: strengthen community-based organisation structures so that they are self-supporting; integrate communities into local ward-level planning; enhance private sector employment opportunities for women; pilot and document new models of security of tenure for wider application in Bangladesh; increase collection of results, and more comprehensively communicate the success and learning the project has created for addressing urban poverty in Bangladesh. The scaled-up activities will also support and add value to the new urban programme following on from UPPR.
What is the additional and total support the UK will provide?
Additional support of £3 million is requested to the UPPR project, bringing the total support to £ 67.7 million. The programme will be extended by 7 months to March 2015.
What are the expected results?
The UPPR project makes a significant contribution to DFID’s global framework results on cash transfers, water and sanitation and hygiene promotion. Effective local social mobilisation is at the core of UPPR’s approach and 98% of participants are women. / The project operates in 7 City Corporations (including Dhaka North and Dhaka South) and 17 municipalities (“Pourashavas”) across Bangladesh. The key activities include: / healthy and secure living environments – created through mobilising community-based organisations (CBOs) in partnership with local government, civil society and the private sector; £24 mill will be spent through Settlement Improvement Funds to provide e.g. safe water, toilets, footpaths, and drainage; / resources, knowledge and skills to increase the incomes and assets of urban poor people; £14.5mill will be spent through Socio-Economic Funds to provide education, apprenticeships, and grants to set up small businesses; particularly for women; / a more supportive national policy environment to address urban poverty – for example developing pro-poor urban policies and strengthening the Bangladesh Urban Forum. / The cost extension, which aims to maximise the impact and sustainability of the project’s overall results, will support activities with the following results: / 6 towns will meet a ‘satisfactory’ score on the programme’s ‘capacity assessment scorecard’ with regard to their Local Government Institutions’ ability to support pro-poor policy development; / 10 additional CDC Clusters[1] will be aligned to ward boundaries and registered with the appropriate authority to better integrate the CDCs into urban planning structures; / 4 additional towns will have developed climate change resilience strategies; / 8 new MOUs will be established with private sector entities to provide employment opportunities to poor women (approx. 2,300) in UPPR settlements on an on-going basis; / 3 new models of security of tenure will have been piloted and documented (for possible use in the new urban poverty programme that DFID is currently designing); and / 7 new qualitative and quantitative outcome and research studies that contribute to the evidence-base of results and best practices.
What is the approach to implementation?
In order to optimise and consolidate the contribution of UPPR to lifting urban poor people out of poverty and integrating them into the wider urban society, a moderate cost extension would give sufficient time for UPPR to ensure the sustainability of structures and results. It would also allow more opportunities to effectively communicate UPPR’s results, best practices and successful tools to those taking over and supporting urban poverty reduction interventions. Six new areas of activities will strengthen the sustainability of the project and provide a platform for any such future interventions. / New activities / 1. Strengthen community organisation structures and build capacity of local government institutions to support pro-poor policy development. / Community-based organisation structures and savings and credit groups at the cluster level will be strengthened through a systematic approach which includes holding elections, conducting Community Action Planning (CAPs) and consolidating and monitoring Savings and Credit group activities and the Operations and Maintenance Fund activities. Stronger, more mature CDC Clusters will be identified and will be supported by UPPR to help build the capacity of weaker CDC Clusters. / UPPR will build capacity of Local Government Institutions (LGIs) to support CDCs and support pro-poor policy. The roles and responsibilities to be assumed by the LGIs will be determined by conducting an institutional analysis and capacity needs assessment. Transfer of responsibilities to LGIs for some functions will follow a prescribed and gradual process which UPPR has designed for the phase-out period and is outlined in Figure 1. To support this transition, there will be on-going technical support from UPPR throughout the extended period. It is planned that the LGIs in all towns will have made progress and that at least six will have ‘satisfactory’ capacity by the end of the extended period in March 2015. / Figure 1: Phases of LGI capacity building process / 2. Integrate community organisations into local ward-level planning to facilitate stronger pro-poor planning by local government. / UPPR has mobilised over 518,000 households into Primary Groups (PGs), Community Development Committees (CDCs a group of 2 – 300 PGs) and CDC Clusters (a total of 254 groupings of CDCs). The project will focus on enhancing the long term sustainability of these structures in four towns (10 Clusters) in order to develop a model for replication for officials in towns across Bangladesh. The activities will involve the realignment of CDCs into formally registered CDC Clusters that are consistent with official local ward level boundaries in order to integrate these communities into the urban structure. It is expected that this will facilitate more effective contribution /influence from poor urban communities into the design of ward and town level plans. It is hoped that the realignment will enable a three tier organisational structure 1) The PG as an informal body at neighbourhood level, 2) the CDC as semi-formal organisation at local ward level; and 3) a ward level governing body. / Individual UPPR beneficiaries would own this ward level organisation and participate through their PGs and CDCs. If this structure proves effective, then the community-based organisations could act as partners (i.e. engage in partnership arrangements with other organisations/institutions) in future urban poverty reduction programmes. / 3. Assess climate change risk and develop resilience strategies in UPPR communities. / An integral component of the extension period will be conducting vulnerability assessments using UPPR Settlement Land Maps (SLMs) at town and ward levels. This will form the basis for development of plans containing measures for adaptation to climate change and enhancing the resilience of poor communities. Based on the available data in the SLMs, areas of assessment will include risk and vulnerability to environmental pollution, epidemics, and disasters, both man-made and natural. / 4. Work with trainees, trainers and employers to help poor urban women access semi-skilled employment. / Building on previous work by UPPR with ILO and following a similar approach to DFID’s Skills and Employment programme, UPPR will undertake intensive sector and sub-sector analysis and subsequently supply chain analysis to explore the employment opportunities for the poor and extreme poor. Participatory analysis to-date sought to establish which sectors have greatest demand for labour. The terms of reference for carrying out a more thorough analysis at the national level have been prepared and UPPR expects to have the results available by January 2014. The outcomes of this study will be used during the remaining period to develop and implement a private sector partnerships strategy and action plan for skills development and employment. A portion of funds has been budgeted for training on the sectors identified in the strategy and to be carried out by partner corporate centres that specialise in relevant areas. / 5. Pilot and document new models of security of tenure which can be replicated by other programmes in Bangladesh / UPPR currently works on developing models for security of tenure through piloting initiatives in several UPPR towns. The project also facilitates UPPR communities to access support to housing and housing finance. An extension will allow additional focus on these activities, which will result in demonstration and documentation of models of security of tenure for poor communities in different contexts across UPPR towns. These documented models of best practice will be disseminated in-line with UPPR’s communication strategy and will inform future programming, thus contributing to longer-term progress and sustainability / 6. Research Evaluation and Communications / The 7 month project extension will enable UPPR Research Evaluation and Learning Unit to build on measuring outputs and outcomes and to more comprehensively communicate evidence-based results, lessons learned, and proven tools for urban poverty reduction planning and sustainability. This is important to addressing widely held misconceptions among policy makers about slums and how to assist the urban poor. / The time extension reduces the pressure to compress multiple data collection activities into a short timeframe. Qualitative studies that show change over time, e.g. women’s empowerment, can be undertaken both in late 2013 and 2014. Outcome studies on activities implemented in 2013 will generate new insights, such as assessing outcome of an improved approach to apprenticeship training and employment in the formal sector. A best practice study will be undertaken each quarter, starting in Q4 of 2013, and continued through the extension period. Beneficiary feedback mechanisms for qualitative outcome assessment of infrastructure improvements to create healthy and secure living environments will be implemented. Implementation of a comprehensive communications strategy to ensure the growing body of results, lessons and best practices are shared widely to the benefit stakeholders and pro-poor urban policy development. / Risk / To mitigate the risk of insufficient government buy-in to the UPPR phase-out/sustainability strategy, UNDP Country Director and Resident Coordinator will personally engage to help drive the agenda forward and secure formal endorsement from each Mayor and council for the joint sustainability activities. As UPPR’s work will be focused at municipal level, any impact from the national election is likely to be at a minimum. Furthermore, UPPR has past experience of working with municipalities during election periods. UPPR is also working to incentivise LGIs to invest in longer-term capacity development by prioritising those towns which commit to co-financing activities. This approach is also being increasingly adopted by other programmes in Bangladesh. Ownership will be further fostered by introducing an element of competition between Local Government Institutions (LGIs) through UPPR’s town grading system. Finally, CDC and CDC Cluster leads will be trained to continue the work and to demand support from LGIs. / Oversight / Throughout the extension period, governance structures such as the National Steering Committee and Project Management Board will be maintained, and, the Mutual Accountability Unit will continue to comprehensively assess compliance with project policies and procedures, including those on anti-corruption and fraud. / VFM / Systematic measurement of Value for Money will be integrated into the new activities from the outset and will be underpinned by an Economy, Efficiency, and Effectiveness approach. The table below sets out indicators and some expected unit costs for the extension period at both the effectiveness and efficiency levels. / Unit costs under extension phase Unit Cost (£) / Overall programme cost 3,000,000 / Effectiveness 1 Cost per towns capably engaged in pro-poor implementation TBD / 2 Cost per ward level plans replicated in other towns TBD / 3 Cost per resilience plans implemented TBD / 4 Cost per job obtained TBD / 5 Cost per land tenure model up-scaled and replicated TBD / Efficiency 1 Cost per town of LGI capacity building 34,938 / 2 Cost per ward level plan developed and implemented 91,806 / 3 Cost per resilience plan developed per town 87,205 / 4 Cost per MOU signed 46,278 / 5 Cost per land tenure models tested and documented 61,204 / 6 Cost per RELU study 36,187 / Economy 1 / Cost per consultancy 15,000 / Cost per workshop 2,500 / Cost per training per person 100 / Cost per Women's Empowerment survey 25,000 / Cost per Savings & Credit group study 20,000 / Cost per staff per month 2,140 / Cost per field trip 100 / Cost per audit 5,000 / Budget / # Activities Activity Breakdown Cost breakdown (GBP) Total (GBP) % allocation / 1 Implementing Sustainability Strategy Public representatives 137,000 700,850 23% / LGI staff 97,750 / LGI systems improvement 101,250 / Community leaders 273,000 / Support to community institutions 46,000 / HQ Recovery Charge 45,850 / Sub-Total 700,850 / 2 Pilot approaches to integrate community organisations into ward-level planning Joint Ward Level Planning & Capacity building 650,000 815,340 27% / SLM & CDC Boundary Demarcation 112,000 / HQ Recovery Charge 53,340 / Sub-Total 815,340 / 3 Community Climate & Resilient Plans Consultants 30,000 246,100 8% / Ward and town level climate change assessments 70,000 / Capacity building for LGIs 25,000 / Capacity building for communities 25,000 / Funds for initiating strategy implementation 80,000 / HQ Recovery Charge 16,100 / Sub-Total 246,100 / 4 Enhanced Engagement with the Private Sector Consultants 30,000 267,500 9% / Workshops 10,000 / Skills Development Training 210,000 / HQ Recovery Charge 17,500 / Sub-Total 267,500 / 5 Land tenure, community planning and housing improvement Capacity building institutionalization of SLM at LGI level 23,000 203,300 7% / Piloting secure tenure models 147,000 / Documentation of tenure and housing improvement process 20,000 / HQ Recovery Charge 13,300 / Sub-Total 203,300 / 6 Research, Evaluation and Learning Unit (RELU) Staff costs for extension 90,000 253,310 8% / Women's Empowerment survey 25,000 / Savings & Credit group study 20,000 / SEF & SIF studies 30,000 / Community Monitoring 19,500 / Best practices studies 15,000 / Climate Change assessment 10,000 / Ward level planning monitoring 10,000 / Communications & Reporting 17,238 / HQ Recovery Charge 16,572 / Sub-Total 253,310 / 7 Management Staff Costs 425,000 513,600 17% / Travel 20,000 / Audit 10,000 / Office running cost 25,000 / HQ Recovery Charge 33,600 / Sub-Total 513,600 / GRAND TOTAL 3,000,000 100% / Phase One / Institutional analysis and capacity assessment lead to development of capacity development plans for LGIs / Phase Two / Gradual institutionalisation of functions in LGIs / Phase Three / Support and technical assistance by UPPR / Phase Four / LGIs run on their own
Describe any key changes to the original business case?
The original Project Memorandum and objectives remain unchanged; the cost extension will support the addition of new activities to strengthen the sustainability of the project’s structures and results during phase-out of the programme.
[1] UPPR mobilises beneficiaries into Primary Groups (PGs) of 20 poor urban households. A Community Development Group/Committee (CDC) is a grouping of 2-300 PGs. A CDC Cluster is a grouping of CDCs.